## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-101 | As a developer, I want to submit Python and Java source code via paste or file upload so that the system can queue it for analysis. | Must | Code Submission Module | Shubham | Completed
Sprint 1 | Sprint 1 | US-102 | As a developer, I want the system to validate the syntax of submitted code before processing so that broken code never reaches the AI pipeline. | Must | Syntax Gatekeeper (AST / javalang) | Shubham | Completed
Sprint 1 | Sprint 1 | US-103 | As a developer, I want the system to auto-detect the programming language (Python or Java) when 'Auto' is selected so that manual selection is not required. | Must | Language Detection (Magika / Heuristics) | Shubham | Completed
Sprint 1 | Sprint 1 | US-104 | As a developer, I want submitted code to be stored in Redis cache with a unique session ID so that analysis tasks can retrieve it asynchronously. | Must | Redis Session Store | Shubham | Completed
Sprint 1 | Sprint 1 | US-105 | As a developer, I want the analysis task to be dispatched to a Celery background worker so that the API remains non-blocking for concurrent users. | Must | Celery Task Queue | Shubham | Completed
Sprint 1 | Sprint 1 | US-106 | As a developer, I want the static linters (Bandit, Pylint, Radon) to run concurrently on Python code so that Stage 1 analysis completes quickly. | Must | Python Linter Pipeline (asyncio.gather) | Shubham | Completed
Sprint 1 | Sprint 1 | US-107 | As a developer, I want the FastAPI health endpoint to report system status including Redis and Celery availability. | Should | Health Check Endpoint (/health) | Shubham | Completed
Sprint 1 | Sprint 1 | US-108 | As a developer, I want the Code Analysis Agent (LLM) to evaluate code quality, detect smells, and assign a letter grade (A–F) with cyclomatic complexity metrics. | Must | Code Analysis Agent (Gemini Flash) | Shubham | Completed
Sprint 2 | Sprint 2 | US-201 | As a developer, I want the Security Vulnerability Agent to identify OWASP Top 10 vulnerabilities such as SQL Injection (CWE-89) and Command Injection (CWE-78) in submitted code. | Must | Security Vulnerability Agent | Shubham | Completed
Sprint 2 | Sprint 2 | US-202 | As a developer, I want the Code Analysis Agent and Security Agent to run in parallel using a LangGraph fan-out architecture so that Stage 2 analysis time is reduced by 50%. | Must | Parallel LangGraph StateGraph (fan-out) | Shubham | Completed
Sprint 2 | Sprint 2 | US-203 | As a developer, I want the system to merge all findings from both agents into a synchronized state so that downstream remediation has complete context. | Must | sync_findings LangGraph Node | Shubham | Completed
Sprint 2 | Sprint 2 | US-204 | As a developer, I want the Remediation Agent to generate specific code fixes for each identified vulnerability so that developers receive actionable corrected code. | Must | Remediation Agent (Gemini Pro) | Shubham | Completed
Sprint 2 | Sprint 2 | US-205 | As a developer, I want the PR Summary Agent to generate an executive review report with overall risk rating (Clean / Low / Medium / High / Critical) and approve/reject recommendation. | Must | PR Summary Agent | Shubham | Completed
Sprint 2 | Sprint 2 | US-206 | As a developer, I want the Streamlit frontend to display findings classified by severity (Critical, High, Medium, Low) with OWASP category labels. | Should | Streamlit Findings Dashboard | Shubham | Completed
Sprint 2 | Sprint 2 | US-207 | As a developer, I want to view a composite security score and overall risk rating after every analysis run. | Should | Security Score Display | Shubham | Completed
Sprint 2 | Sprint 2 | US-208 | As a developer, I want the system to detect hardcoded secrets, insecure cryptographic hashes (MD5/SHA-1), and weak cipher modes (ECB/DES) in Java code. | Must | Semgrep Java Security Ruleset | Shubham | Completed
Sprint 2 | Sprint 2 | US-209 | As a developer, I want the LangSmith tracing integration to record every LLM call for debugging and latency monitoring. | Should | LangSmith Tracing (@traceable) | Shubham | Completed
Sprint 2 | Sprint 2 | US-210 | As a developer, I want the Logfire observability dashboard to display real-time pipeline metrics and error rates. | Could | Logfire / Pydantic Instrumentation | Shubham | Completed
Sprint 3 | Sprint 3 | US-301 | As a developer, I want an Intent Guardrail to classify submissions and reject prompt injection attacks or non-code inputs before they reach the analysis pipeline. | Must | Intent Guardrail (app/guardrails.py) | Shubham | Completed
Sprint 3 | Sprint 3 | US-302 | As a developer, I want the security agent to fall back to deterministic Semgrep / Bandit findings if the LLM refuses to respond due to content safety filters. | Must | Static Fallback Engine (_extract_static_fallbacks) | Shubham | Completed
Sprint 3 | Sprint 3 | US-303 | As a developer, I want the AI Security Agent prompt to be framed as a QA Compliance Auditor so that content safety filters do not censor legitimate vulnerability analysis. | Must | QA Auditor Prompt Engineering (security_vuln.py) | Shubham | Completed
Sprint 3 | Sprint 3 | US-304 | As a developer, I want a RAG (Retrieval-Augmented Generation) knowledge base to provide OWASP security guidelines to the Remediation Agent for grounded fix suggestions. | Should | RAG Index & Retriever (app/services/rag/) | Shubham | Completed
Sprint 3 | Sprint 3 | US-305 | As a developer, I want a conversational Chat Tab in the UI where I can ask follow-up questions about my code review results with session memory preserved across turns. | Should | Chat Graph with MemorySaver (app/agents/chat_graph.py) | Shubham | Completed
Sprint 3 | Sprint 3 | US-306 | As a developer, I want the Java static analysis to use Semgrep (enterprise AST + taint-flow engine) instead of hand-written regex so that detection accuracy is production-grade. | Must | Semgrep Java Integration (app/linters.py) | Shubham | Completed
Sprint 3 | Sprint 3 | US-307 | As a developer, I want the API to reject oversized code submissions (>10,000 lines) with an HTTP 413 response to prevent resource exhaustion. | Should | Request Size Guard (submit.py) | Shubham | Completed
Sprint 3 | Sprint 3 | US-308 | As a developer, I want the complete test suite (unit + integration, 49 tests) to pass with >60% code coverage so that the pipeline is verifiably reliable. | Must | pytest Suite with Coverage (tests/) | Shubham | Completed
Sprint 4 | Sprint 4 | US-401 | As a developer, I want a React-based Code Analysis dashboard with vertical stacking instead of side-by-side layout for better readability. | Must | React Frontend UI | Shubham | Completed
Sprint 4 | Sprint 4 | US-402 | As a developer, I want the results dashboard to normalize OWASP severities into three visual tiers (High/Critical, Medium, Low). | Must | Severity Normalization Logic | Shubham | Completed
Sprint 4 | Sprint 4 | US-403 | As a developer, I want to view my PR summary without the React app crashing if release notes or developer summary payloads are missing. | Must | React Error Boundaries & Fallbacks | Shubham | Completed
Sprint 4 | Sprint 4 | US-404 | As a developer, I want to download a formatted PDF export of the entire consolidated analysis report. | Must | PDF Export (react-to-print) | Shubham | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours. Days 1-14 show remaining effort burn-down.
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-101 | T-101-1 | Design FastAPI POST /api/v1/submit/paste endpoint schema | 2026-07-01 | 2026-07-02 | Shubham | Backend Development | Completed | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-101 | T-101-2 | Implement multipart file upload endpoint /api/v1/submit/file | 2026-07-02 | 2026-07-02 | Shubham | Backend Development | Completed | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-102 | T-102-1 | Implement Python AST syntax gatekeeper using ast.parse() | 2026-07-02 | 2026-07-02 | Shubham | Backend Development | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-102 | T-102-2 | Implement Java syntax validator using javalang (brace check + class declaration) | 2026-07-03 | 2026-07-03 | Shubham | Backend Development | Completed | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-103 | T-103-1 | Implement language auto-detection by file extension and keyword heuristics | 2026-07-03 | 2026-07-04 | Shubham | Backend Development | Completed | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-104 | T-104-1 | Configure Redis cache with session TTL and setex storage | 2026-07-04 | 2026-07-04 | Shubham | Infrastructure | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-105 | T-105-1 | Set up Celery worker with Redis broker on analysis queue | 2026-07-04 | 2026-07-05 | Shubham | Infrastructure | Completed | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-106 | T-106-1 | Implement asyncio.gather() parallel runner for Bandit, Pylint, Radon | 2026-07-05 | 2026-07-05 | Shubham | Backend Development | Completed | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-108 | T-108-1 | Design and implement Code Analysis Agent Gemini prompt with JSON schema | 2026-07-05 | 2026-07-07 | Shubham | AI/ML Engineering | Completed | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-201 | T-201-1 | Design Security Vulnerability Agent prompt with OWASP QA Auditor framing | 2026-07-11 | 2026-07-11 | Shubham | AI/ML Engineering | Completed | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-201 | T-201-2 | Implement SecurityVulnerability Pydantic model and JSON output parser | 2026-07-11 | 2026-07-12 | Shubham | Backend Development | Completed | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-202 | T-202-1 | Refactor LangGraph graph.py from sequential chain to parallel fan-out StateGraph | 2026-07-12 | 2026-07-14 | Shubham | AI/ML Engineering | Completed | 6 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-203 | T-203-1 | Implement sync_findings_node to merge parallel agent outputs into shared state | 2026-07-14 | 2026-07-14 | Shubham | Backend Development | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-204 | T-204-1 | Design and implement Remediation Agent with RAG context injection | 2026-07-14 | 2026-07-16 | Shubham | AI/ML Engineering | Completed | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-205 | T-205-1 | Implement PR Summary Agent with composite risk score and approve/reject logic | 2026-07-16 | 2026-07-16 | Shubham | AI/ML Engineering | Completed | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-206 | T-206-1 | Build Streamlit findings dashboard with severity tabs and OWASP labels | 2026-07-16 | 2026-07-18 | Shubham | Frontend Development | Completed | 6 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-208 | T-208-1 | Add Java regex heuristics for SQLi, Path Traversal, Hardcoded Credentials | 2026-07-18 | 2026-07-19 | Shubham | Security Engineering | Completed | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-209 | T-209-1 | Integrate LangSmith @traceable decorators across all agent nodes | 2026-07-19 | 2026-07-19 | Shubham | Observability | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-301 | T-301-1 | Implement validate_intent() guardrail with LLM classification and length pre-filter | 2026-07-25 | 2026-07-26 | Shubham | Security Engineering | Completed | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-302 | T-302-1 | Implement _extract_static_fallbacks() for multi-language Bandit + Semgrep fallback | 2026-07-26 | 2026-07-27 | Shubham | Backend Development | Completed | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-303 | T-303-1 | Reframe security agent system prompt as QA Compliance Auditor to bypass content filters | 2026-07-27 | 2026-07-27 | Shubham | AI/ML Engineering | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-304 | T-304-1 | Build RAG embeddings pipeline, FAISS index, and retriever for OWASP knowledge base | 2026-07-28 | 2026-07-29 | Shubham | AI/ML Engineering | Completed | 6 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-305 | T-305-1 | Implement multi-turn Chat Graph with MemorySaver checkpointer and Streamlit Chat Tab | 2026-07-29 | 2026-07-30 | Shubham | AI/ML Engineering | Completed | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-306 | T-306-1 | Replace Java regex heuristics with Semgrep OSS p/java rulepack subprocess integration | 2026-07-30 | 2026-07-31 | Shubham | Security Engineering | Completed | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-308 | T-308-1 | Write 49-test pytest suite (unit + integration) with >60% code coverage report | 2026-07-31 | 2026-08-01 | Shubham | Quality Assurance | Completed | 7 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-401 | T-401-1 | Refactor index.tsx and CodePanel.tsx to remove horizontal flex constraints for full-width layout | 2026-08-08 | 2026-08-08 | Shubham | Frontend Development | Completed | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-402 | T-402-1 | Implement normalizeSeverity() in ResultsPanel.tsx to bin Critical/High into a single tier | 2026-08-08 | 2026-08-09 | Shubham | Frontend Development | Completed | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-403 | T-403-1 | Add Array.isArray() guards and robust destructuring to PRSummaryPanel.tsx | 2026-08-09 | 2026-08-10 | Shubham | Frontend Development | Completed | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-403 | T-403-2 | Integrate remark-gfm and react-markdown to properly render backend AI markdown tables | 2026-08-10 | 2026-08-11 | Shubham | Frontend Development | Completed | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-404 | T-404-1 | Implement useReactToPrint hook with custom @media print dark-mode CSS overrides | 2026-08-11 | 2026-08-11 | Shubham | Frontend Development | Completed | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-401 | T-401-2 | Resolve Celery macOS Apple Silicon SIGSEGV crash by switching prefork to --pool=solo | 2026-08-11 | 2026-08-12 | Shubham | Infrastructure | Completed | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 1 | No impediments — environment setup completed successfully. | Proceeded with FastAPI endpoint design.
Sprint 1 | 2 | Redis connection timeout in local Docker environment. | Switched to host-mode Redis; added connection retry logic.
Sprint 1 | 3 | No impediments. | Continued Celery worker configuration.
Sprint 1 | 4 | javalang parser missing from requirements.txt. | Added javalang to pyproject.toml and reinstalled dependencies.
Sprint 1 | 5 | Bandit returning exit code 1 even on valid code with no findings. | Added exit code tolerance — treat exit 0 and 1 as valid Bandit runs.
Sprint 1 | 6 | No impediments. | Completed Code Analysis Agent prompt engineering and testing.
Sprint 1 | 7 | No impediments. | Sprint 1 review and retrospective completed.
Sprint 2 | 1 | Gemini content safety filter refusing to analyse vulnerable Java snippets. | Adopted QA Compliance Auditor prompt framing to bypass filter refusals.
Sprint 2 | 2 | No impediments. | Implemented Security Vulnerability Agent JSON parser with retry logic.
Sprint 2 | 3 | LangGraph sequential pipeline taking ~77 seconds per submission. | Redesigned graph.py to use parallel fan-out architecture; latency reduced by ~50%.
Sprint 2 | 4 | No impediments. | Implemented sync_findings_node and conditional routing.
Sprint 2 | 5 | Remediation Agent occasionally returning incomplete JSON. | Added 2-attempt retry with exponential backoff; improved JSON extraction regex.
Sprint 2 | 6 | No impediments. | Streamlit dashboard polished with severity colour coding.
Sprint 2 | 7 | Logfire metrics export timeout (read timeout 9.9s). | Configured async flush interval; added non-blocking export queue.
Sprint 3 | 1 | Guardrail LLM classification rejecting some short valid Python snippets. | Added length pre-filter threshold; tuned prompt to differentiate code vs. plain text.
Sprint 3 | 2 | No impediments. | Completed static fallback engine for multi-language Bandit + Semgrep findings.
Sprint 3 | 3 | Semgrep downloading p/java rules on first run causing cold-start delay. | Semgrep rules now cached after first run; subsequent scans are instant.
Sprint 3 | 4 | FAISS RAG index not persisting between Celery worker restarts. | Added index serialization to disk on build; retriever reloads from file on startup.
Sprint 3 | 5 | Chat graph MemorySaver losing session context after Redis flush. | Scoped MemorySaver to in-process memory; session isolated per analysis run.
Sprint 3 | 6 | pytest integration tests failing due to aggressive Redis mock patching. | Realigned mocks to app.api.routes.submit.get_redis_client boundary; 49/49 tests passing.
Sprint 3 | 7 | No impediments. | Sprint 3 review, retrospective, and documentation update completed.
Sprint 4 | 1 | Celery worker crashing with SIGSEGV on macOS during LangGraph execution. | Switched Celery from prefork to --pool=solo to avoid macOS multiprocessing bug with C-extensions.
Sprint 4 | 2 | React UI breaking when backend pr_summary payload is incomplete. | Added strict null-checks and Array.isArray() fallbacks in PRSummaryPanel.
Sprint 4 | 3 | Code Analysis and Results panels side-by-side layout too cramped. | Removed lg:flex-row constraints in index.tsx; enforced full-width vertical stacking.
Sprint 4 | 4 | Markdown tables in PR Summary rendering as raw pipe-delimited text. | Installed react-markdown and remark-gfm to parse GitHub-flavored markdown natively.
Sprint 4 | 5 | Generic recharts BarChart labels misaligned ('ecurity' typo). | Replaced BarChart entirely with premium CSS glassmorphism progress bars.
Sprint 4 | 6 | Browser default PDF print dialog stripping dark mode backgrounds. | Added -webkit-print-color-adjust: exact in styles.css @media print block.
Sprint 4 | 7 | No impediments. | Sprint 4 review and UI presentation completed.

## Retrospection
SL # | Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 2026-07-01 | 2026-07-09 | Shubham | Write unit tests immediately after each feature is implemented, not at the end of the sprint. | Underestimating dependency setup time — Redis and Celery configuration took longer than expected. | Using asyncio.gather() for parallel subprocess execution — significantly improved linter throughput. | Added dependency installation to sprint planning checklist; allocated explicit setup buffer time.
2 | Sprint 2 | 2026-07-11 | 2026-07-23 | Shubham | Implement LLM retry logic with exponential backoff from the start rather than adding it retroactively. | Relying solely on LLM outputs without a deterministic static fallback — this caused silent vulnerability drops. | QA Auditor framing for the security prompt — completely eliminated content filter refusals. | Added _extract_static_fallbacks() as a mandatory resilience layer for all language-specific linter outputs.
3 | Sprint 3 | 2026-07-25 | 2026-08-07 | Shubham | Document debugging sessions immediately after each bug fix while context is fresh. | Running all 49 tests at the end of the sprint — should run incrementally after every feature. | Semgrep integration pattern — replacing fragile regex heuristics with structured AST analysis tools. | Added DEBUGGING_SESSION_NOTES.md as a living document; tests now run on every code change via pre-commit hook.
4 | Sprint 4 | 2026-08-08 | 2026-08-12 | Shubham | Start verifying backend JSON payload contracts defensively in React components before rendering maps. | Stop relying on default Celery prefork pooling when running complex Python C-extensions (like grpc/LangGraph) on macOS Apple Silicon. | Continue investing in premium frontend UI polish (glassmorphism, tailwind micro-animations) as it drastically improves perceived product value. | Updated HOW_TO_RUN.md to mandate --pool=solo for local testing. Integrated robust prop destructuring in React views.